## Matryca logiczna
PROJECT LOGICAL FRAME
| Logics of intervention | Objectively verifiable | Other sources and means of | Assumptions
|  | coefficients | verification
Overall | What are the general objectives | What are the main coefficients | What are the sources
Objectives | to which the project shall contribute? | related to the general obejctives? | of information for those coefficients?
| Amelioration of operating efficiency for medical emergency services within the cross-boarder area between Poland and Russia by modernisation of the despatchment base for medical emergency teams and increasing the standards of services provided by the Provincial Integrated Hospital in Elbląg and the City Ambulance Station in Kaliningrad. | 1. Modernisation and rebuilding of the despatchment base for the Medical Emergency Unit of the Provincial Integrated Hospital in Elbląg 2 Being in possession of ECG data distant transmission systems. 3. Purchasing of ambulances | 1. Modernised despatchment base - commissioned by means of commissioning report. 2. Created system - acknowledged by means of commissioning report. 3. Invoice, commissioning report
Specific | What detailed objective | What coefficients clearly indicate | What are the sources of existing | What factors and conditions
objective | contributing to meeting the general objectives | that the project's objective | or possible information to be collected? | outside the Beneficiary's liability are
| shall be reached by the project? | has been achieved? | What are the methods of verification? | indispensable to reach the objective? (external conditions)
| Shortening the time to reach a patient who requires assistance and granting them with complex medical aid in the first minutes after a life threatening incident has occurred Amelioration of decision supporting system in the incidents of sudden life threatening by launching the system for distant data transmission Tele_ECG and ambulance localisation Enhancing the qualifications for medical emergency staff within the cross-boarder area by acquiring and reinforcing professional skills of life saving by them on the basis of international standards. | 1.Until the end of 2013, shortening by 10% the time between receiving the call by the team and reaching a patient by them. 2. Performing at least 30 transmissions of ECG data per month to a specialised cardiological centre (this will help to take the decision to transport a patient to a correct centre - hospital).Until now the teams have not performed that procedure. 3. 32 persons (128participans) trained in international standards of proceedings in medical life saving | 1. Verification based on the despatchment cards- Medical Emergency Unit of the provincial Integrated Hospital in Elbląg 2. The number of ECG data transmissions performed from the places of interventions. 3. Project documents: meetings, trainings required for getting the information? | Reaching the detailed objectives of the project depends on specified conditions, which remain outside the Beneficiary's or partner's control. The factors are as follows: - tendency to prioritise some sectors of healthcare at the expense of medical emergency services; - uncertain economic situation during project realisation; -in the context of market surroundings, competitive , new products, pressure from public opinion and authorities; changes in the clients' requirements- law - changes in the law, acts, administrative decisions, new norms and certificates; - new technical solutions - discoveries, technological progress, new tools and technologies shall influence various activities and lead to modifications - social and political factors - political crisis, natural catastrophes, local protests, lack of prosperity may be the reason for many actions
What risks should
be taken into consideration?
During project planning there may appear various types of risk which should be taken into consideration: Economic risk: Source of financing - due to project rejection during selection there is a risk that not all activities will be completed, which will influence the successfulness of the project. Political risk is caused by changes in local a for the project. Social risks are related to: - problems with encouraging the target groups to participate in the project; - lack of interest in the project from the society.
Expected | Results comprise the products assumed | What coefficients may be used | What are the sources of information | What external conditins must be
results | in order for a detailed objective to be achieved. | to measure whether , and to what extent, | about those coeffcients? | fulfilled in order to achieve the planned results?
| What are expected results? | did the project achieve the expected results?
| 1.1 Amelioration of accesibility of medical infrastructure and better efficiency of services 2.1 Shortening the time needed to reach a patient and making an immediate diagnosis due to distant transmission of ECG data, ambulance monitoring. 3.1 Quicker providing the services for the patients from accidents 4.1 Creation of better educational infrastructure for paramedics and other staff of emergency services 5.1 Better sharing of good practices within the area of international standards for emergency services Making common standards in medical life saving operations 6.1 Creating common standards in nedical life saring 7.1 Enhancing the level of knowledge regarding IT systems in Kaliningrad, ECG data transmission; 8. Increased awareness and knowledge of the society regarding first aid. | 1.1The number of modernised bases for Medical Emergency Services - 1 2.1. The number of healthcare centres equipped with additional systems for data transmission, systems for ambulance localisation - 1 3.1. The number of ambulances purchased – 5 3.2. Purchase of automated non-invasive cardiac massage device – 7 pieces 4.1 The number of modernised rooms adapted and equipped for the training purposes – 1 5.1 The number of persons involved in interregional project by participation in periodical trainings and meeting - 104 6. 1. Cross-boarder meetings – 4 7.1 The number of trainings – 2 (lasting 2 days each) 8.1 The number of informative and promotional campaigns – 2 (City Town Hall in Elbląg, Department of Education) 8.2 The number of comics related to first aid - 50000 | Coefficients to formulate common standards in regional medical emergency services Reports: Periodical reports from project implementation. Documentation and training materials from project actions. | The following conditions is expected to achieve the planned results: - efficient promotion for regional leaders and representatives of various partner organisations in order to underline the necessity to realise the project - evaluation of cooperation between public healthcare centres at cross-boarder level, - analysis of current status of infrastructure and the needs of the patients in the region, -positive reaction to the initiatives planned by medical personnel In line with the general principles of good management one should counteract the consequences of sudden situations and events by: *proper definition of objectives, resources, project coefficients * involvement and support of the organistions supporting the project * maintaining relations with the project partners, communication of results of the projects *well selectedand experienced staff with adequate knowledge and skills *well-prepared plann and schedule, task delegating to staff
*risk monitoring and control of the project *proper and timely reporting about various actions *proper communication in the project * solving the most difficult problems at the highest level of management
Activities | What key activities should be realised and in what order | Means: | What are the sources of information | What are the necessary conditions
| , in order for the expected results to be achieved? | What means are required | about progress in the project. | before the project starts?
| (group the activities according to the results) | to realise the activities, e.g.. |  | What conditions beyond the Beneficiary's control
|  | staff, equipment, trainings | Costs | shall be fulfilled to realise the planned actions?
|  | elaborated materials, operational base | What are the action costs?
How are they classified?
| The following activities should be realised during the project realisation: - formulation of the project team - allocation of staff; - adaptation, modernisation and reconstruction of a building located at 6 Orzeszkowa street in Elbląg for the needs of Medical Emergency Unit of the Provincial Integrated Hospital in Elbląg; - extension of the decision supporting system, the system for ambulance localisation in Elblag and Kaliningrad; - purchasing the new ambulances with equipment - defibrillators with ECG data distant transmission - for the Provincial Integrated Hospital in Elbląg, - modernisation of the conference hall in the Provincial Integrated Hospital in Elbląg. The hall will be subject to renovation ( ceilings, wall and floor covering, etc) and equipped with devices needed for trainings - chairs, desks, boards, multimedia devices, phantoms, coffee maker, etc.; -Meetings of the project team in Poland - 3 meetings lasting 2 days each; -Meetings of the project team in Russia - 3 meetings lasting 2 days each; | Means: Staff: Applicant: constant members of staff: 1147 Medical emergency unit : 7 nurses, ambulance crews: 25 doctors, 49 paramedics, 27 drivers from the Transportation Unit . The Department consists of 11 teams: 4 basic ones and 3 specialist ones, neontological, night duty, holiday healthcare, transportation between the hospitals, sanitary transportation. Additionally: Night and holiday duties Partner no 1 656 Medical staff: 381 Educational dimension: -trainings regarding ECG data transmission - trainings regarding modern IT systems | Progress in the project will be monitored on the basis of: progress reports, final report, notes, minutes and official notes Reports on the actions: -meetings of the project team; Mass media: press and TV. Project realisation. Promotional campaign and project actions, as well as the results of dissemination: -comics about first aid for school children and the youth aged 8-18 years old - purchasing the communication tools: informative boards, press articles and TV campaign in local and regional media , office materials with logo and information regarding the funds, etc. | It is indispensable to identify the following necessary conditions: - identification and justification of the necessity to realise the project, - identification of support level and involvement in the initiative, - defining the range of actions for various project participants , specification of common elements for cooperation
| Training regarding distant ECG data transmission for the paramedics of the Provincial Integrated Hospital In Elbląg and the City Ambulance Station in Kaliningrad - The training regarding computer systems of the City Ambulance Station in Kaliningrad for the paramedics of the dispatchers from the Provincial Integrated Hospital - Training regarding European standards of medical life saving for the paramedics of the City Ambulance Station in Kaliningrad - Creation of joint project team between the City Ambulance Station in Kaliningrad and the Provincial Integrated Hospital in Elbląg and formulation of common standards in medical life-saving – meeting held in Poland - Creation of joint project team between the City Ambulance Station in Kaliningrad and the Provincial Integrated Hospital in Elbląg and formulation of common standards in medical life-saving – meeting held in Russia - Promotional actions: publication of a comics - Project summary – meeting in Poland | Transfer of knowledge and sharing the experience: - meeting of the project team in Kaliningrad - staff visit regarding sharing the ideas for establishing common standards for medical emergency services in the region - a meeting to summarise the project Equipment: - securing the basic activities of the project Material resources: transport, administrative costs, trip costs, purchasing specialists ambulances with equipment for educational purposes. Other: Printing services, internet and communication tools: comics regarding first aid for school children and the youth aged 8-18 years old | Means allocation: 1. Human resources - 115 400,40 euro 2. Business trips -4 025,00 euro 3. Equipment and supplies - 1 059 779,33 euro 4. Domestic office - 0,00 5. Other costs, services - 104 910,11 euro 6. Works - 904 271,43 euro Total: 2 188 386,27 euro